## Architecture Modules
Module 1 - UI/UX Design
Responsive Web Design (RWD)
Wireframing
Prototyping
Testing and Iteration
Module 2 - Application Authentication/Authorization
Authentication:
Credential Management
Session Management
Cross-Site Request Forgery Protection
Logging Authentication Activity (Audit Trails of Login/Logout)
Authorization:
Security Groups: Registered Users/Managers/Administrators
Role-based/ Claims-based/Policy-based/Resource-based/View-based Authorization
Policy Enforcement Points for Major Components of the Application Under Consideration
Authorization Scalability and Latency
Module 3 - User Login/Registration/Forgot Password
Login User:
Registration/Login/Forgot Password
Logged in User:
Pages Load
Pages Edit
Module 4 - Email Integration
SendGrid or MailKit or SMTP

## Estimation
Module 1 - UI/UX Design | Estimation in Man Hours
Software Development - Coding and Unit Testing | 35
QA - Testing | 14
Pre-Production/Production/Deployment | 14
UAT | 14
Module 2 - Application Authentication/Authorization
Software Development - Coding and Unit Testing | 70
Database Development - Scripting | 35
QA - Testing | 35
Pre-Production/Production/Deployment | 35
UAT | 21
Module 3 - Login/Registration/Forgot Password
Software Development - Coding and Unit Testing | 140
Database Development - Scripting | 70
QA - Testing | 70
Pre-Production/Production/Deployment | 70
UAT | 35
Module 4 - Email Integration
Software Development - Coding and Unit Testing | 105
Database Development - Scripting | 51
QA - Testing | 51
Pre-Production/Production/Deployment | 51
UAT | 28